## Sprint 2
| Positive | Improvement | Owner | Action
Lam | Team's Spirit is good | Process is slow, need to finish CMS by Wednesday | All | Apply what you have leant to tasks
| Back-end work very hard to have API soon | Leak of contact with customer (Mr. Huy) --> busy | All | Ask customer via email
| Design is good (Ms. Thao worked very hard) | Complicated history on code. --> Define a branch, commit name convesion | Quy | Define conventions for git commit
Tai | Come to meeting ontime | Need time to done a task
Apply knowledge to work
Quoc | devoted to work, finished tasks ontime | avoid code smell | All
get used to backend part
teamwork productivity is improved
Khang | Requirements are more clear | OT, stress | Khang
Learn and apply knowledge to project successfully
Thao | Regular scrum on time | It takes long time for review the task of UI/ UX design J | Ky, Thanh
| Enthusiastic supporting from every team members | Preparing for demonstration is not very well. | Thao, Thanh
Quy | Willing learning | Finish task ontime
| Hard working | Improve estimation | All
|  | Read document carefully | All
Trung
Thanh | Welcome Thao to the team - Start UI/UX design | Not follow adding spent time and estimate for tasks | All
| Finalize requirement | Improve GIT flow | Quy
Good progress
Support each other
Open Actions

## Sprint 1
| Positive | Improvement |  | Owner | Action
Lam | Mentor support enthusiastically | Don't finish task on time | -1 | All | Improve estimate skill
| comfortable asmostphere | Not have a PO, so it's difficult to have a right road map | 1 | All | Thanh: Ask Huy about communicate via email
Tai | Complete all assigned tasks | Still no estimate of the time it takes to complete a task | -1 | All
| Good support from technical leaders | Take long time to finish a task | -1 | All
|  | Lack of knowledgement | 1 | All
Quoc | Work harded | Teamwork skills still not good | 1 | All
|  | Go to the meeting on time | 1 | All
|  | Update the notifications as soon as posible | 1 | All
Khang | Complete tasks assigned | process of project |  | Thanh
Improve team work skill
Learn some new tools and techniques
Quy
Trung | Good team working | Should care more about development environment |  | All
Everyone join all phases of the project
Get familiar with real working environment
Thanh | Good clarify requirement discussion | UI/UX designer is not avaiable | 1 | Thanh
| Good progress | Add estimation and spending time for the task | -1 | All
|  | Be on time in demo meeting | 1 | All
|  | Review task | 1 | Technical leaders
Open Actions