## Sprint 1
| Positive | Improvement | Owner | Action
Lam | Mentor support enthusiastically | Don't finish task on time | All | Improve estimate skill
| comfortable asmostphere | Not have a PO, so it's difficult to have a right road map | All | Thanh: Ask Huy about communicate via email
Tai | Complete all assigned tasks | Still no estimate of the time it takes to complete a task | All
| Good support from technical leaders | Take long time to finish a task | All
|  | Lack of knowledgement | All
Quoc | Work harded | Teamwork skills still not good | All
|  | Go to the meeting on time | All
|  | Update the notifications as soon as posible | All
Khang | Complete tasks assigned | process of project | Thanh
Improve team work skill
Learn some new tools and techniques
Quy
Trung | Good team working | Should care more about development environment | All
Everyone join all phases of the project
Get familiar with real working environment
Thanh | Good clarify requirement discussion | UI/UX designer is not avaiable | Thanh
| Good progress | Add estimation and spending time for the task | All
|  | Be on time in demo meeting | All
|  | Review task | Technical leaders
Open Actions