## Sprint 6
| Positive | Improvement | Owner | Action
Tai
| Use English in Scrum meeting | School Schedule | Tai, Quoc | Flexible and register working hour and can compensate later
Quoc
Khang | Had a new server and new prospective members | the progress is slower because Lam was not in the team
Good progress
Used English in scrum meeting
Thao | The process goes smoothly | Long list of reviewing on trello | Trung and Thanh | Ask help from other colleagues
Good cooperation members
Great suporting from marketing side about content
Hard working team ^^
Quy
Trung | We're getting more members | Put more effort on code review
| Deadline have been adjusted | Put more detail on commit message | Trung | Send article about how to create good commit message
| Made some step on navigation improvement | (Should have on Phase 2) Plan to switch to use git flow | Trung | Transfering working way about git flow
Start to use English in Scrum
Thanh | Welcome new members Tung and Minh | Review tasks
| Customer happy with landing page design | Handle cases when internet conection is lost. | All | Pay attention in unhappy cases
App more stable
Open Actions

## Sprint 3&4
| Positive | Improvement |  | Owner | Action
Lam | Done basically CMS System | Slow learning process on Xamarin and MVVMCross --> Finish tasks slow--> Can not finish for the demo section in this spring | 0 | All | Discuss with technical leader before executing task
| Have a real server, deploy API and CMS --> Auto deploy or just manually? | Have no roadmap to learn and do Xamarin task and native knowledge --> Just research and do the tasks--> Risk to meet bugs in the future | 0 | All | Ask help from technical leader for unclear things
| Follow git flow good, use the united git flow | My code is not clear --> Need to have a task to refactor code | 0 | All | Discuss with technical leader to figure out the solution
UI Design almost finished
Tai | Start to use Estimated time in Trello | Need to work harder, to better understand about Xamarin. | 0 | Developer Team | Understand what you did
| Working Process have been fasten a little bit | Need to arrange working time. (Bcs I've to go to school next week) | 1 | Thanh | Create online sheet to register working time, reschedule meetings
Expand Knowledge (Xamarin)
Supporters Help me a lot with the brand new language (Xamarin)
Quoc | Add estimated and spent task's time | refactor code | 1 | All | ask technical leader first and Create task on ToDO in the trello later
finished needed tasks
worked hard
Khang | Facilitate members to take chance to become fullstack + mobile developer at the same time | understanding how the things work or code monkey is more important
Learn and apply knowledge to project successfully
Thao | Regular scrum on time | UI/UX Design time and knowledge | 1 | Thao | Learning
Enthusiastic supporting from every team members
Clear process
Quy | Finished most tasks | Review task |  | Leaders
Hard working
Trung | Despite of time and many challenges, We did some very impressive progress | I will try to arrange more time for this project
| Discuss together to figure out the suitable solution | Lot of things to do (including navigation, popup…etc) | 1 | Thanh | Plan
We're getting more helps from other people like Khoa
Thanh | Good progress | Attempt to confine the technical discussion during scrum meeting | 1 | All
Start to implement application on IOS and Android
Open Actions

## Sprint 2
| Positive | Improvement |  | Owner | Action
Lam | Team's Spirit is good | Process is slow, need to finish CMS by Wednesday | 1 | All | Apply what you have leant to tasks
| Back-end work very hard to have API soon | Leak of contact with customer (Mr. Huy) --> busy | 1 | All | Ask customer via email
| Design is good (Ms. Thao worked very hard) | Complicated history on code. --> Define a branch, commit name convesion |  | Trung | Define conventions for git commit
Tai | Come to meeting ontime | Need time to done a task
Apply knowledge to work
Quoc | devoted to work, finished tasks ontime | avoid code smell |  | All
get used to backend part
teamwork productivity is improved
Khang | Requirements are more clear | OT, stress |  | Khang
Learn and apply knowledge to project successfully
Thao | Regular scrum on time | It takes long time for review the task of UI/ UX design J |  | Ky, Thanh
| Enthusiastic supporting from every team members | Preparing for demonstration is not very well. |  | Thao, Thanh
Quy | Willing learning | Finish task ontime
| Hard working | Improve estimation |  | All
|  | Read document carefully |  | All
Trung
Thanh | Welcome Thao to the team - Start UI/UX design | Not follow adding spent time and estimate for tasks |  | All
| Finalize requirement | Improve GIT flow |  | Quy
Good progress
Support each other
Open Actions

## Sprint 1
| Positive | Improvement |  | Owner | Action
Lam | Mentor support enthusiastically | Don't finish task on time | -1 | All | Improve estimate skill
| comfortable asmostphere | Not have a PO, so it's difficult to have a right road map | 1 | All | Thanh: Ask Huy about communicate via email
Tai | Complete all assigned tasks | Still no estimate of the time it takes to complete a task | -1 | All
| Good support from technical leaders | Take long time to finish a task | -1 | All
|  | Lack of knowledgement | 1 | All
Quoc | Work harded | Teamwork skills still not good | 1 | All
|  | Go to the meeting on time | 1 | All
|  | Update the notifications as soon as posible | 1 | All
Khang | Complete tasks assigned | process of project |  | Thanh
Improve team work skill
Learn some new tools and techniques
Quy
Trung | Good team working | Should care more about development environment |  | All
Everyone join all phases of the project
Get familiar with real working environment
Thanh | Good clarify requirement discussion | UI/UX designer is not avaiable | 1 | Thanh
| Good progress | Add estimation and spending time for the task | -1 | All
|  | Be on time in demo meeting | 1 | All
|  | Review task | 1 | Technical leaders
Open Actions